## Sheet1
Dunadd Community Council
Action Register
Action | Raised | Owner | Next steps | Update | Status
Traffic calming measures - Kilmartin Main | Ongoing | HF | As Kilmartin road has been resurfaced, HF asked if they were going to do the lines again. | Response from roads Jan 24 - – The lining contractors will be attending to reinstate the markings however it is a weather dependent task therefore we are unable to advise exactly when this will be | Ongoing
Traffic calming measures - Barrmor View | Ongoing | HF | In January 24 HF asked - Barrmor View- is there any update if there will be any traffic calming measures installed or a right turn warning triangle installed on the main road? - | Response from roads - The Traffic and Development Officer has advised there are no plans to lower the speed restriction. The road is a block paved shared area. Drivers should be driving at an appropriate speed and anybody witnessed breaking this should be reported to Police Scotland. A warning triangle is not required as there is sufficient forward visibility and the junction is within a 30mph speed restriction. | Ongoing
C38 - horse signs | 2022-11-01 | HF | Email sent Jan for update | Response - We have received confirmation that this invoice has been paid and we will aim to have these installed before the end of the financial year. | Ongoing
DP is waiting for an update from the roads team at the Council regarding the hedge that looks onto the footpath | 2023-09-01 | DP | DP contacting council | Jan 24 -We can confirm that an officer was out and we can confirm that the footpath is not being restricted. We will make contact with Scottish Water and ask them to take action before the path is restricted. | Closed
It was noted that this week there have been coaches blocking the road accessing the museum and also parking in the bus stop. HF to speak to police and DP to check what the legal stance is on parking in bus stops and also who owns that land. | 2023-09-01 | HF&DP | HF sent update out Sep 23 - the police have advised that the traffic wardens can manage this however we don’t have any traffic warders in the area. Nov 23 - it was asked at the meeting if a local person could become a volunteer warden - DP asking the Council. | Feb 24 - response advising a local person could not become a volunteer warden but if a role became available, would be able to apply. | Ongoing
HF to find out when the next landowners meeting will be | 2023-09-01 | HF | HF emailed on 15th November - no response, another email sent 25th January. | Jan 24 - HF has sent a follow up email no response as yet | Ongoing
HF to get a new date for defib training | 2023-11-01 | HF | Ongoing | ongoing | ongoing
HF will make contact with the representative for Mid Argyll (Timber transport group re the C38.) | 2023-11-01 | HF | Email sent 21st Nov and follow up on 25th January | Feb 24 - response received - DCC to send feedback for the next meeting in April | Ongoing
Questions re floods 6/7th October | 2023-11-01 | HF | HF sent questions in | Response put on website and socials end of December - discussion in January meeting | Ongoing
HF to request that there are signs on the road of the bus stop in Kilmartin and ask could a local resident volunteer and become a traffic warden? | 2023-11-01 | HF | DB asking re traffic warden. | Response from roads team - This request is being considered and the transport team have been liaising with the Traffic and Development colleagues. A site visit will be arranged at the start of the new financial year once new budgets become available. | Ongoing
HF to ask what is the difference between an advisory or a compulsory 20 mph limit | 2023-11-01 | HF | Email sent Jan | Response from roads team - An advisory 20 mph speed restriction is something like the Twenty’s Plenty signs and road markings, the 20 mph speed restrictions are not legally enforceable. Compulsory speed restrictions are legally enforceable as they have what is called a TRO, a Traffic Regulation Order. I have attached a copy of the Council’s Road Speed Limit Policy Framework, for info. | Ongoing
Dalriada footpath - HF, DS and SW to have a conversation re next steps. | 2023-11-01 |  | Meeting in Dec unfortunately DCC could not attend but have minutes - will keep everyone updated. |  | Ongoing